## Project Manager Portfolio Data
Project Master Data: Community-Based Offline Learning Companion App
1. Work Breakdown Structure (Tasks & Scheduling)
Use this sheet to practice NETWORKDAYS, Gantt Charting (via Conditional Formatting), and Status Tracking.
Task ID | Phase | Task Name | Assigned To | Start Date | End Date | Status | % Complete | Priority
TSK-001 | Discovery | Stakeholder Interviews (Desamind) | Rahmat | 2026-05-01 | 2026-05-05 | Completed | 100% | High
TSK-002 | Discovery | Community Needs Assessment | Ahmad | 2026-05-03 | 2026-05-10 | Completed | 100% | High
TSK-003 | Discovery | Technical Feasibility Study (Offline Sync) | Siti | 2026-05-06 | 2026-05-12 | In Progress | 60% | Medium
TSK-004 | Design | UI/UX Low-Fi Wireframes | Rahmat | 2026-05-13 | 2026-05-20 | In Progress | 40% | High
TSK-005 | Design | Educational Content Architecture | Dewi | 2026-05-15 | 2026-05-25 | Not Started | 0% | Medium
TSK-006 | Development | Database Schema Design | Siti | 2026-05-26 | 2026-06-05 | Not Started | 0% | High
TSK-007 | Development | PWA Offline Storage Implementation | Siti | 2026-06-01 | 2026-06-15 | Not Started | 0% | High
TSK-008 | Development | User Authentication Module | Ahmad | 2026-06-10 | 2026-06-20 | Not Started | 0% | Medium
TSK-009 | Development | Content Sync Module | Siti | 2026-06-15 | 2026-07-05 | Not Started | 0% | High
TSK-010 | Content | Primary Education Module Upload | Dewi | 2026-07-01 | 2026-07-15 | Not Started | 0% | Medium
TSK-011 | QA/Testing | Alpha Testing (Internal) | Rahmat | 2026-07-16 | 2026-07-25 | Not Started | 0% | High
TSK-012 | QA/Testing | Beta Testing (Community) | Ahmad | 2026-07-26 | 2026-08-10 | Not Started | 0% | High
TSK-013 | Deployment | Final Launch Preparation | Rahmat | 2026-08-11 | 2026-08-15 | Not Started | 0% | High
TSK-014 | Support | User Training Documentation | Dewi | 2026-08-15 | 2026-08-30 | Not Started | 0% | Low
2. Financial & Budgeting Ledger
Use this sheet for SUMIFS (Total by Category), XLOOKUP (Rate lookup), and Variance Analysis.
Item ID | Category | Description | Estimated Cost ($) | Actual Cost ($) | Payment Status | Vendor
FIN-001 | Infrastructure | Cloud Hosting (Firebase) | 500 | 480 | Paid | Google
FIN-002 | Design | Figma Professional License | 150 | 150 | Paid | Figma
FIN-003 | Development | Contractor: Database Specialist | 2000 | 2200 | Partial | Freelance-S
FIN-004 | Development | PWA Components Library | 300 | 300 | Paid | Vendor-X
FIN-005 | Content | Subject Matter Expert Fees | 1200 | 1200 | Pending | Expert-A
FIN-006 | Marketing | Community Outreach Kits | 800 | 950 | Paid | PrintShop
FIN-007 | Infrastructure | Offline Server Hardware (RasPi) | 400 | 420 | Paid | LocalStore
FIN-008 | Admin | LPDP Documentation Fees | 100 | 50 | Paid | Internal
3. Risk Register
Use this for Weighted Scores and Data Validation lists.
Risk ID | Category | Risk Description | Impact (1-5) | Probability (1-5) | Mitigation Strategy
RSK-001 | Technical | Sync conflict with slow internet | 5 | 4 | Implement last-write-wins protocol
RSK-002 | Adoption | Low community participation | 4 | 2 | Incentivize top learners
RSK-003 | Budget | API costs exceeding limit | 3 | 3 | Set hard alerts and limits
RSK-004 | Legal | Data privacy compliance | 5 | 1 | Encrypt all local user data
References
Community-Based Offline Learning Companion App Project Overview